## Gantt Chart Week 1-5
Project Name: AdaptAble
Team Name: Autotuner
Team Members |  | Project Start Date: | 2025-02-11
Cade Gouker
Samantha Fung
Ian Wright
Ronald Kline
Truong Bui
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5
Project Stage | Task | Start Date | End Date | Assignee | Status | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | s
Project Definition | Team Formation | 2025-02-11 | 2025-02-11 | Truong Bui | Completed
| Create Team Contract | 2025-02-11 | 2025-02-18 | Truong Bui | Completed
| Define Team Roles & Responsibilities | 2025-02-11 | 2025-02-18 | Truong Bui | Completed
| Research Accessible Toy Designs | 2025-02-18 | 2025-02-25 | Ian Wright | Completed
| Identify Market Gap & Needs | 2025-02-18 | 2025-02-25 | Cade Gouker | Completed
| Draft Project Definition Report | 2025-02-18 | 2025-02-25 | Truong Bui | Completed
Product Definition | Identify Customers | 2025-02-25 | 2025-03-04 | Samantha Fung | Completed
| Contact Expert for Advice to Determine Our Customers Requirement | 2025-02-25 | 2025-03-04 | Truong Bui | Completed
| Determine the Criteria for a Successful Toy | 2025-03-04 | 2025-03-11 | Ronald Kline | Completed
| Evaluate Criteria Using Decision Matrix | 2025-03-04 | 2025-03-11 | Ian Wright | Completed
| Complete QFD (Quality Function Deployment) | 2025-03-04 | 2025-03-11 | Cade Gouker | Completed
| Evaluate the Most Important Criteria | 2025-03-04 | 2025-03-11 | Samantha Fung | Completed
Conceptual Design | Create a Main Function of the Toy | 2025-03-06 | 2025-03-06 | Ronald Kline | Completed
| Brainstorm Product Concepts that allow Toy to follow its Function | 2025-03-06 | 2025-03-25 | Ronald Kline | Completed
| Evaluate the Product Concepts with a Pugh Matrix | 2025-03-06 | 2025-03-25 | Truong Bui | Completed
| Create Project Progress Presentation Slides | 2025-03-25 | 2025-04-01 | Truong Bui | Completed
| Review and Refine Slides | 2025-03-25 | 2025-04-01 | Samantha Fung | Completed
| Deliver Project Progress Presentation | 2025-03-25 | 2025-04-01 | Ronald Kline | Completed
| Finalize Conceptual Drawing | 2025-04-02 | 2025-04-15 | Ronald Kline | Completed
| Research Available Magnet | 2025-04-02 | 2025-04-15 | Truong Bui | Completed
| Research into Textural Material | 2025-04-02 | 2025-04-15 | Samantha Fung | Completed
Product Development | Meet with higher-up (Dr. Mollica) for Project Clarification | 2025-04-16 | 2025-04-16 | Ian Wright | Completed
| Contact Expert for Advice for Design Ideas | 2025-04-17 | 2025-04-21 | Truong Bui | Completed
| Use SOLIDWORKS to 3D Model Parts | 2025-04-17 | 2025-04-21 | Cade Gouker | Completed
| Order or Print Parts | 2025-04-21 | 2025-05-01 | Ian Wright | Completed
| Assemble First Prototype | 2025-04-24 | 2025-05-01 | Samantha Fung | Completed
| Test Prototype Functionality | 2025-04-29 | 2025-05-01 | Ronald Kline | Completed
| Identify Improvements to Refine CAD | 2025-05-01 | 2025-05-06 | Truong Bui | Completed
| Oder additional Parts | 2025-05-05 | 2025-05-09 | Ian Wright | Completed
| Assemble Final Prototype | 2025-05-07 | 2025-05-12 | Samantha Fung | Completed
| Conduct Final Testing | 2025-05-12 | 2025-05-13 | Ronald Kline | Completed
Product Support | Design Poster for Final Prototype | 2025-04-24 | 2025-05-13 | Cade Gouker | Completed
| Submit Poster (if printed by instructors) | 2025-04-24 | 2025-05-13 | Truong Bui | Completed
| Deliver the Poster | 2025-05-15 | 2025-05-15 | Ronald Kline | Completed
| Draft Final Report | 2025-04-29 | 2025-05-21 | Truong Bui | In-Progress
| Review & Revise Final Report | 2025-04-29 | 2025-05-21 | Cade Gouker | In-Progress
| Deliver Final Report | 2025-05-21 | 2025-05-21 | Ronald Kline | Not Started

## Gantt Chart Week 6-10
Project Name: AdaptAble
Team Name: Autotuner
Team Members |  | Project Start Date: | 2025-02-11
Cade Gouker
Samantha Fung
Ian Wright
Ronald Kline
Truong Bui
[6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
Project Stage | Task | Start Date | End Date | Assignee | Status | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27
Project Definition | Team Formation | 2025-02-11 | 2025-02-11 | Truong Bui | Completed
| Create Team Contract | 2025-02-11 | 2025-02-18 | Truong Bui | Completed
| Define Team Roles & Responsibilities | 2025-02-11 | 2025-02-18 | Truong Bui | Completed
| Research Accessible Toy Designs | 2025-02-18 | 2025-02-25 | Ian Wright | Completed
| Identify Market Gap & Needs | 2025-02-18 | 2025-02-25 | Cade Gouker | Completed
| Draft Project Definition Report | 2025-02-18 | 2025-02-25 | Truong Bui | Completed
Product Definition | Identify Customers | 2025-02-25 | 2025-03-04 | Samantha Fung | Completed
| Contact Expert for Advice to Determine Our Customers Requirement | 2025-02-25 | 2025-03-04 | Truong Bui | Completed
| Determine the Criteria for a Successful Toy | 2025-03-04 | 2025-03-11 | Ronald Kline | Completed
| Evaluate Criteria Using Decision Matrix | 2025-03-04 | 2025-03-11 | Ian Wright | Completed
| Complete QFD (Quality Function Deployment) | 2025-03-04 | 2025-03-11 | Cade Gouker | Completed
| Evaluate the Most Important Criteria | 2025-03-04 | 2025-03-11 | Samantha Fung | Completed
Conceptual Design | Create a Main Function of the Toy | 2025-03-06 | 2025-03-25 | Ronald Kline | Completed
| Brainstorm Product Concepts that allow Toy to follow its Function | 2025-03-06 | 2025-03-25 | Ronald Kline | Completed
| Evaluate the Product Concepts with a Pugh Matrix | 2025-03-06 | 2025-03-25 | Truong Bui | Completed
| Create Project Progress Presentation Slides | 2025-03-25 | 2025-04-01 | Truong Bui | Completed
| Review and Refine Slides | 2025-03-25 | 2025-04-01 | Samantha Fung | Completed
| Deliver Project Progress Presentation | 2025-03-25 | 2025-04-01 | Ronald Kline | Completed
| Finalize Conceptual Drawing | 2025-04-02 | 2025-04-15 | Ronald Kline | Completed
| Research Available Magnet | 2025-04-02 | 2025-04-15 | Truong Bui | Completed
| Research into Textural Material | 2025-04-02 | 2025-04-15 | Samantha Fung | Completed
Product Development | Meet with higher-up (Dr. Mollica) for Project Clarification | 2025-04-16 | 2025-04-16 | Ian Wright | Completed
| Contact Expert for Advice for Design Ideas | 2025-04-17 | 2025-04-21 | Truong Bui | Completed
| Use SOLIDWORKS to 3D Model Parts | 2025-04-17 | 2025-04-21 | Cade Gouker | Completed
| Order or Print Parts | 2025-04-21 | 2025-05-01 | Ian Wright | Completed
| Assemble First Prototype | 2025-04-24 | 2025-05-01 | Samantha Fung | Completed
| Test Prototype Functionality | 2025-04-29 | 2025-05-01 | Ronald Kline | Completed
| Identify Improvements to Refine CAD | 2025-05-01 | 2025-05-06 | Truong Bui | Completed
| Oder additional Parts | 2025-05-05 | 2025-05-09 | Ian Wright | Completed
| Assemble Final Prototype | 2025-05-07 | 2025-05-12 | Samantha Fung | Completed
| Conduct Final Testing | 2025-05-12 | 2025-05-13 | Ronald Kline | Completed
Product Support | Design Poster for Final Prototype | 2025-04-24 | 2025-05-13 | Cade Gouker | Completed
| Submit Poster (if printed by instructors) | 2025-04-24 | 2025-05-13 | Truong Bui | Completed
| Deliver the Poster | 2025-05-15 | 2025-05-15 | Ronald Kline | Completed
| Draft Final Report | 2025-04-29 | 2025-05-21 | Truong Bui | In-Progress
| Review & Revise Final Report | 2025-04-29 | 2025-05-21 | Cade Gouker | In-Progress
| Deliver Final Report | 2025-05-21 | 2025-05-21 | Ronald Kline | Not Started

## Gantt Chart 11-15
Project Name: AdaptAble
Team Name: Autotuner
Team Members |  | Project Start Date: | 2025-02-11
Cade Gouker
Samantha Fung
Ian Wright
Ronald Kline
Truong Bui
[6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
Project Stage | Task | Start Date | End Date | Assignee | Status | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01
Product Development | Order or Print Parts | 2025-04-21 | 2025-05-01 | Ian Wright | Completed
| Assemble First Prototype | 2025-04-24 | 2025-05-01 | Samantha Fung | Completed
| Test Prototype Functionality | 2025-04-29 | 2025-05-01 | Ronald Kline | Completed
| Identify Improvements to Refine CAD | 2025-05-01 | 2025-05-06 | Truong Bui | Completed
| Oder additional Parts | 2025-05-05 | 2025-05-09 | Ian Wright | Completed
| Assemble Final Prototype | 2025-05-07 | 2025-05-12 | Samantha Fung | Completed
| Conduct Final Testing | 2025-05-12 | 2025-05-13 | Ronald Kline | Completed
| Design Poster for Final Prototype | 2025-04-24 | 2025-05-13 | Cade Gouker | Completed
| Submit Poster (if printed by instructors) | 2025-04-24 | 2025-05-13 | Truong Bui | Completed
| Deliver the Poster | 2025-05-15 | 2025-05-15 | Ronald Kline | Completed
Product Support | Draft Final Report | 2025-04-29 | 2025-05-21 | Truong Bui | In-Progress
| Review & Revise Final Report | 2025-04-29 | 2025-05-21 | Cade Gouker | In-Progress
| Deliver Final Report | 2025-05-21 | 2025-05-21 | Ronald Kline | Not Started
| Review and Refine Slides | 2025-03-25 | 2025-04-01 | Samantha Fung | Completed
| Deliver Project Progress Presentation | 2025-03-25 | 2025-04-01 | Ronald Kline | Completed
| Finalize Conceptual Drawing | 2025-04-02 | 2025-04-15 | Ronald Kline | Completed
| Research Available Magnet | 2025-04-02 | 2025-04-15 | Truong Bui | Completed
| Research into Textural Material | 2025-04-02 | 2025-04-15 | Samantha Fung | Completed
| Meet with higher-up (Dr. Mollica) for Project Clarification | 2025-04-16 | 2025-04-16 | Ian Wright | Completed
| Contact Expert for Advice for Design Ideas | 2025-04-17 | 2025-04-21 | Truong Bui | Completed
| Use SOLIDWORKS to 3D Model Parts | 2025-04-17 | 2025-04-21 | Cade Gouker | Completed
Product Development | Order or Print Parts | 2025-04-21 | 2025-05-01 | Ian Wright | Completed
| Assemble First Prototype | 2025-04-24 | 2025-05-01 | Samantha Fung | Completed
| Test Prototype Functionality | 2025-04-29 | 2025-05-01 | Ronald Kline | Completed
| Identify Improvements to Refine CAD | 2025-05-01 | 2025-05-06 | Truong Bui | Completed
| Oder additional Parts | 2025-05-05 | 2025-05-09 | Ian Wright | Completed
| Assemble Final Prototype | 2025-05-07 | 2025-05-12 | Samantha Fung | Completed
| Conduct Final Testing | 2025-05-12 | 2025-05-13 | Ronald Kline | Completed
| Design Poster for Final Prototype | 2025-04-24 | 2025-05-13 | Cade Gouker | Completed
| Submit Poster (if printed by instructors) | 2025-04-24 | 2025-05-13 | Truong Bui | Completed
| Deliver the Poster | 2025-05-15 | 2025-05-15 | Ronald Kline | Completed
Product Support | Draft Final Report | 2025-04-29 | 2025-05-21 | Truong Bui | In-Progress
| Review & Revise Final Report | 2025-04-29 | 2025-05-21 | Cade Gouker | In-Progress
| Deliver Final Report | 2025-05-21 | 2025-05-21 | Ronald Kline | Not Started